SIERRA LEONE COUNTRY PRESENTATION

NEXT STEPS

| Activity | Responsible | Timeframe |
| --- | --- | --- |
| Debrief Top Management | Deputy CMO | 15th July 2013 |
| Debrief RCH TCC on Newborn Global Health Action Plan and UN Commission on Life Saving Commodities -set up working groups to finalize country bottlenecks -Propose consultation -Identify and recruit consultant to populate bottleneck tool and finalize report | Deputy CMO/Director RCH | 18th July 2013 |
| Convene 2 days country consultation to discuss and agree on the bottlenecks, and provide input to the Global Every Newborn Draft Action Plan -one day working session -Follow-up meetings for the next one month | Deputy CMO/Director RCH | 24th -25 th July 2013 |
| Complete UN Commission on Life Saving Commodities Proposal and submit | Deputy CMO /Director RCH/H4+ | By 15th August 2013 |
| Finalize and complete bottleneck analysis tool | DCMO /Director RCH/ Consultant | By August 22nd2013 |
| Prepare, finalize and submit report of consultation process to the Global Action Group on newborn and give feedback on Global Newborn Action Plan | DCMO/Director RCH/Consultant | By August 22nd 2013 |
| Follow up on actions from the recently concluded National Newborn Advocacy Forum held on 12th June 2013 | DCMO/Director RCH |  |